## Sheet1
Project Name: Online Course for Students |  | Presented by: Amit Harish Doddamani |  | Date: | 2023-06-14
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 5 | 20 | 100 |  |  | $- | 100 |  | 100
2. Planning | 4 | 30 | 120 |  |  | $- | 120 |  | 120
3. Executing |  |  | $- |  |  | $- | $- |  | $-
3.1 Course design and development |  |  | $- |  |  | $- | $- |  | $-
3.1.1 Supplier management training | 4 | 10 | 40 | 2 | 10 | 20 | 60 | 40 | 100
3.1.2 Negotiating skills training | 5 | 10 | 50 | 2 | 10 | 20 | 70 | 30 | 100
3.1.3 Project management training | 4 | 10 | 40 | 2 | 10 | 20 | 60 | 50 | 110
3.1.4 Software applications training | 5 | 10 | 50 | 4 | 20 | 80 | 130 | 100 | 230
3.1.5 Software testing | 8 | 20 | 160 | 4 | 15 | 60 | 220 | 80 | 300
3.2 Course administration | 3 | 10 | 30 | 1 | 20 | 20 | 50 | 100 | 150
3.3.Course evaluation | 5 | 30 | 150 |  |  | $- | 150 | 150 | 300
3.4 Stakeholder communications | 3 | 30 | 90 |  |  | $- | 90 |  | 90
4. Monitoring and Controlling | 5 | 10 | 50 |  |  | $- | 50 |  | 50
5. Closing | 5 | 10 | 50 |  |  | $- | 50 |  | 50
Subtotal | [8 empty] | 1700
Reserves |  |  | $- |  |  | $- | $- |  | 300
Total | 56 |  | 930 | 25 | 85 | 220 | 1150 | 550 | 2000
Note: We have reserves of 15 % which accounts to 300$